## Slide 1: TIRZ #4 North Beach Projects in Process
May 12, 2026

## Slide 2
Las Casitas Del Mar
Project Update | 
Address | 4606 Gulfbreeze Blvd, Corpus Christi, TX 78402
Description | Project includes the construction of 14 new multi family units for rental.
Project Update | Developer is in the process of rebidding materials for the project. Utility rough-ins and connections have been secured for the site. The developer is also working on the installation of concrete driveways from the street to the development. In addition, the developer is coordinating with the City’s Engineering Department to utilize excess soil from other North Beach projects. This approach would allow usable material to be redistributed within North Beach rather than being hauled off site.
Approved Incentive | North Beach Living Initiative Program- $140,000 Project Specific Development Program- $229,883
Completion Date | July 31, 2027

## Slide 3
North Beach History Plaza
Project Update | 
Address | 2892 N Shoreline Blvd, Corpus Christi, TX 78402
Description | Project includes entryway monument signage, shade structures, and site lighting.
Project Update | The Parks and Recreation Department has engaged Gignac Architect engineering firm. The project is currently at 90% design.
Approved TIRZ Funding | $200,000
Completion Date | FY 2027

## Slide 4
Double Tree by Hilton
Project Update | 
Address | 3200 Surfside Blvd, Corpus Christi, TX 78402
Description | Project includes converting a large meeting room into six luxury suites, including one presidential suite, building a new concrete parking lot with at least 10 spaces and replacing 45 existing balcony doors with upgraded hurricane rated sliding doors.
Project Update | Developer has completed all major interior construction, including texturing, painting, flooring, plumbing, and electrical work, along with bathroom renovations and shower glass installations. The remaining scope primarily consists of final finish-out items, including chandelier lighting installation, furniture and fixture placement, and carpeting installation.
Approved Incentive | North Beach Property Improvement Program- $398,970
Completion Date | December 31, 2026

## Slide 5: Thank you!